## Detailed_Tasks
Main Module | API Endpoint | Task ID | Task Name | Detailed Description | Owner | Priority | Planned Start | Planned End | Actual End | Status | % Complete | Comments / Notes | Last Updated
NATAL | /natal/build-chart | 1.1 | Contract finalize | Freeze request/response JSON, add examples | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.2 | DTOs | Create Pydantic models for input/output | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.3 | Validation | Validate timezone, lat/lon, and date/time | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.4 | Service Logic | Compute planets, signs, houses | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.5 | Controller | Create FastAPI route with metadata headers | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.6 | Tests - Unit | Unit tests for core logic | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.7 | Tests - Contract | Match OpenAPI schema validation | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.8 | Perf Check | Benchmark response time | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.9 | Docs | Prepare API documentation examples | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/build-chart | 1.10 | Definition of Done | Confirm CI/CD pipeline passes and coverage >90% | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.1 | Contract finalize | Define aspect label, strength, and traits | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.2 | Orbs profile | Config for orbs per planet/aspect | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.3 | Aspect Engine | Compute aspects and strengths | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.4 | Characteristics | Map traits from rules file | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.5 | Controller | API implementation | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.6 | Tests | Write boundary and regression tests | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.7 | Docs | Document aspect strength logic | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/aspects | 3.8 | Definition of Done | Validated and merged | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.1 | Contract finalize | Define KPI outputs and description | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.2 | KPI Framework | Map placements to KPI | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.3 | Narrative Builder | Generate deterministic text | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.4 | Controller | API route | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.5 | Tests | KPI and text output validation | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.6 | Docs | Explain KPI mapping | Parakram |  |  |  |  | Completed | 0
NATAL | /natal/characteristics | 4.7 | Definition of Done | Merged and tested | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.1 | Contract finalize | Define life events output structure | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.2 | Transit Rules | Create rules for event detection | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.3 | Window Solver | Compute event windows | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.4 | Event Ranker | Assign major/minor scoring | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.5 | Pagination | Implement cursor and 206 support | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.6 | Tests | Unit tests for life event logic | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.7 | Docs | Document event system | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/life-events | 5.8 | Definition of Done | Merged and validated | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.1 | Contract finalize | Define timeline and summary outputs | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.2 | Timeline Build | Generate items and AI summary | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.3 | Pagination | Add cursor for partial results | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.4 | Tests | Validate logic | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.5 | Docs | Explain timeline creation | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/timeline | 6.6 | Definition of Done | Merged and validated | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.1 | Contract finalize | Define areas and color scheme | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.2 | Scoring Map | Assign GREEN/RED status | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.3 | Generator | Compute summary | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.4 | Controller | API route | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.5 | Tests | Write unit tests | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.6 | Docs | Document output format | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/daily-weekly | 7.7 | Definition of Done | Validated | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.1 | Contract finalize | Define event format | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.2 | Finder | Scan months ahead | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.3 | Controller | Implement API | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.4 | Tests | Write validation tests | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.5 | Docs | Describe event categories | Parakram |  |  |  |  | Completed | 0
REPORTS | /reports/upcoming-events | 8.6 | Definition of Done | Merged | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.1 | Contract finalize | Define compatibility response structure | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.2 | Pair Engine | Compute synastry aspects | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.3 | KPI Scoring | Aggregate KPI weights | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.4 | Narrative | Generate summary text | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.5 | Controller | API endpoint | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.6 | Tests | Validate results | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.7 | Docs | Add documentation | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/synastry | 9.8 | Definition of Done | Merged | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.1 | Contract finalize | Define group output format | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.2 | Pairwise Matrix | Compute pairwise synastry | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.3 | Harmony Model | Group harmony calculation | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.4 | Controller | API endpoint | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.5 | Tests | Add group test cases | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.6 | Docs | Describe visualization | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/group | 10.7 | Definition of Done | Validated | Parakram |  |  |  |  | Completed | 0
COMPATIBILITY | /compat/soulmate-finder | 11.1 | Contract finalize | Define soulmate output format | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.2 | Search Space | Define DOB range | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.3 | Scorer | Implement matching logic | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.4 | Controller | API route | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.5 | Tests | Add deterministic test cases | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.6 | Docs | Explain ethical boundaries | Parakram |  |  |  |  | Not Started | 0
COMPATIBILITY | /compat/soulmate-finder | 11.7 | Definition of Done | Validated | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.1 | Contract finalize | Freeze dignities response format | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.2 | Rules Config | Create YAML for essential dignities | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.3 | Calculator | Implement dignity computation logic | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.4 | Controller | Implement API endpoint | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.5 | Tests | Write tests for dignities | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.6 | Docs | Explain scoring method | Parakram |  |  |  |  | Not Started | 0
NATAL | /natal/dignities-table | 2.7 | Definition of Done | Validated and merged | Parakram |  |  |  |  | Not Started | 0

## Summary_Dashboard
Main Module | APIs | Total Tasks | Completed | In Progress | Not Started | Progress %
NATAL | 4 | 31 | 0 | 0 | 31 | 0
REPORTS | 4 | 28 | 0 | 0 | 28 | 0
COMPATIBILITY | 3 | 22 | 0 | 0 | 22 | 0

## Sheet1
No. | Factor |  | Description (as per text) | Dominant Planetary Aspect(s) Responsible | Explanation
1 | Varna | Varna: | Spiritual & mental balance, mutual respect, non-dominance | Sun–Jupiter (Trine / Sextile) | Sun signifies ego & vitality; Jupiter gives wisdom. A harmonious aspect ensures mutual respect, spiritual balance, and shared values.
|  | : |  | Mercury–Jupiter (Conjunction / Trine)
2 | Vashya | Vashya: | Control, dominance, mutual influence | Mars–Venus (Square / Opposition) | Mars brings assertiveness; Venus governs harmony. Their aspect determines dominance or cooperation. Sun–Moon balance shows mutual influence.
|  | : |  | Sun–Moon (Conjunction / Trine)
3 | Tara | Tara: | Health, longevity, general wellbeing | Sun–Moon (Trine / Sextile) | Moon rules body and emotions; Jupiter gives protection and vitality. Their harmony indicates physical and emotional health in marriage.
|  | : |  | Moon–Jupiter (Trine / Conjunction)
4 | Yoni | Yoni: | Physical attraction & intimacy | Venus–Mars (Conjunction / Trine) | Venus and Mars together drive sexual chemistry and desire, while Venus–Moon aspects nurture emotional closeness.
|  | : |  | Venus–Moon (Trine)
5 | Rasyadhipati | Rasyadhipati: | Friendship, mental connection, intellectual sync | Mercury–Moon (Trine / Sextile) | Mercury symbolizes communication, while Moon and Jupiter govern emotional and philosophical understanding. These aspects build friendship and dialogue.
|  | : |  | Mercury–Jupiter (Trine)
6 | Gana | Gana: | Nature, temperament, and behavioral compatibility | Sun–Mars (Trine / Sextile) | Gana shows temperament; Sun–Mars relates to vitality and courage, while Moon–Saturn reflects emotional maturity and patience.
|  | : |  | Moon–Saturn (Trine / Opposition)
7 | Rashi | Rashi: | Emotional harmony and empathy | Moon–Venus (Conjunction / Trine) | Rashi (Moon sign) is ruled by the Moon; its link with Venus or Neptune shows emotional bonding, empathy, and understanding.
|  | : |  | Moon–Neptune (Trine)
8 | Nandi (Nadi) | Nandi (Nadi): | Health of progeny, fertility, life energy | Sun–Moon (Trine / Sextile) | Jupiter represents fertility and expansion, Venus governs reproduction and love; their harmony favors progeny and happy family life.
|  | : |  | Jupiter–Venus (Trine / Sextile)